## Sheet1
Project Title |  | Start Date |  |  |  |  | Project Duration
Interactive Website for Cricket Updates |  | 2024-09-09 |  |  |  |  | 67
Project Manager |  | End Date
KEG/IT/2324/F/00234 - Aadhil |  | 2024-11-15
# | Task | Start Date | End Date | Duration | Task Status | Remarks
1 | Create the project proposal & video | 2024-09-09 | 2024-11-09 | 2 | Complete
2 | Gain proficiency in HTML, CSS, and JavaScript | [6 empty] | Task Status
2.1 | Learn HTML fundamentals | 2024-11-09 | 13/9/2024 | 2 | Complete |  |  | Complete
2.2 | Develop skills in CSS | 13/9/2024 | 23/9/2024 | 10 | Complete |  |  | In Progress
2.3 | Master JavaScript | 23/9/2024 | 2024-03-10 | 10 | Complete | Focus on dynamic content |  | Not Started
3 | Gather and analyze cricket events updates
3.1 | Understand the audience core needs | 2024-03-10 | 2024-05-10 | 2 | Complete
3.2 | Confirm the project scope with above needs | 2024-05-10 | 2024-07-10 | 2 | Complete
4 | Create the index page | 2024-07-10 | 17/10/2024 | 10 | Complete
5 | Design the graphics for the website | 17/10/2024 | 27/10/2024 | 10 | Not Started
6 | Design and implement additional web pages | 27/10/2024 | 2024-06-11 | 10 | Not Started
7 | Debug the code to resolve errors | 2024-06-11 | 13/11/2024 | 7 | Not Started
8 | Complete and finalize the website | 13/11/2024 | 15/11/2024 | 2 | Not Started