## Sheet1
Project Title |  | Start Date |  |  |  |  | Project Duration
Interactive Website for English Tuition |  | 2024-08-15 |  |  |  |  | 93
Project Manager |  | End Date
KEG/IT/2023/F/0010 - Kalai |  | 2024-11-15
# | Task | Start Date | End Date | Duration | Task Status | Remarks
1 | Create the project proposal & video | 2024-08-15 | 2024-08-25 | 10 | Complete
2 | Gain proficiency in HTML, CSS, and JavaScript | [6 empty] | Task Status
2.1 | Learn HTML fundamentals | 2024-08-30 | 2024-09-09 | 10 | Complete |  |  | Complete
2.2 | Develop skills in CSS | 2024-09-10 | 2024-09-20 | 10 | Complete |  |  | In Progress
2.3 | Master JavaScript | 2024-09-21 | 2024-10-01 | 10 | Complete | Focus on dynamic content |  | Not Started
3 | Gather and analyze client requirements
3.1 | Understand the client’s core needs | 2024-10-02 | 2024-10-04 | 2 | Complete
3.2 | Confirm the project scope with his needs | 2024-10-05 | 2024-10-07 | 2 | Complete
4 | Create the index page | 2024-10-08 | 2024-10-18 | 10 | Complete
5 | Design the graphics for the website | 2024-10-19 | 2024-10-29 | 10 | Not Started
6 | Design and implement additional web pages | 2024-10-30 | 2024-11-04 | 5 | Not Started
7 | Debug the code to resolve errors | 2024-11-05 | 2024-11-07 | 2 | Not Started
8 | Complete and finalize the website | 2024-11-08 | 2024-11-10 | 2 | Not Started